## Sheet1
Sr. No. | Date | Reported Date | Project | Reporter | Task Type | PYN ID | Module/Feature | Task/Issue Summary | Severity | Priority | Queue | Status | Planned Hours(HH:MM) | Actual Time Spent (HH:MM) | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Go Live Date | Closed Date | Comments
1 | 25-10-2017 | 25-10-2017 | World Avenues | Client | Client Issue | WA-186 | Payments | CAN'T ALLOCATE | Critical | P1 | Dev | Open |  | 30 minutes | 25-10-2017 | 25-10-2017 | 25-10-2017 | 25-10-2017 | 25-10-2017 | 25-10-2017
2 | 25-10-2017 | 16-10-2017 | World Avenues | Client | Client Issue | WA-174 | Supplier | W2M Performance | Major | P2 | Client | ReOpned |  | 30 minutes | 17-10-2017 | 17-10-2017
3 | 25-10-2017 | 31-08-2017 | World Avenues | Client | Task | WA-86 | Receipt | Can't download payments report | Medium | P3 | QA | Closed |  | 30 minutes | 22-09-2017 | 22-09-2017 | 23-09-2017 | 25-10-2017 | 25-10-2017 | 25-10-2017
4 | 25-10-2017 | 25-10-2017 | Project | QA | Calls/Meeting |  | All | Disucssion with Developer regarding assigned PYN | Major | P1 | Dev | Closed |  | 1 hour | 25-10-2017 | 25-10-2017 | 25-10-2017 | 25-10-2017 |  |  | Task discussion
5 | 25-10-2017 | 16-10-2017 | World Avenues | Client | Client Issue | WA-168 | Booking | I1011055 | Major | P1 | Client | ReOpned |  | 30 minutes | 12-10-2017 | 16-10-2017 | Not decided |  |  |  | Awaiting for client response
6 | 25-10-2017 | 24-10-2017 | Asian Overland | Client | Calls/Meeting | AOS-426 | Booking | Asia Heavens Floatin deposit agent | Critical | P1 | Dev | Closed |  | 1 hour 30 minutes
7 | 25-10-2017 | 25-10-2017 | Asian Overland | PM | Task |  | Email | Auto Check Supplier Report | Minor | P3 | QA | Closed |  | 15 minutes
8 | 25-10-2017 | 25-10-2017 | Asian Overland | PM | Task | AOS-434 | Agent Exchnage Currency | Agent Exchnage Currency | Major | P1 | QA | Closed |  | 15 minutes | [6 empty] | Created flow diagram
9 | 25-10-2017 | 07-10-2017 | Product | QA | Bug | OTR-311 | Upload Document | Upload Option not provided for online supplier | Major | P2 | QA | Closed |  | 15 minutes | [6 empty] | Verified and updated pyn
10 | 25-10-2017 | 22-09-2017 | PYN | QA | Bug | PYN-87 | Change Log | Details to be displayed in the same way as entered or pasted | Major | P2 | QA | Closed |  | 15 minutes | 22-09-2017 | 25-09-2017 | 27-09-2017 | 25-10-2017 | 25-10-2017 |  | Verified and updated pyn
11 | 25-10-2017 | 09-09-2017 | World Avenues | Client | Calls/Meeting | WA-113 | Email | GTA booking Cancelled immediately: 23304709 | Major | P2 | Dev | ReOpned |  | 20 minutes | 25-09-2017 | 02-10-2017 | 26-09-2017 |  |  |  | Verfied and reopened the case
12 | 25-10-2017 | 25-10-2017 | Product | QA | Calls/Meeting |  | Mapping | City Mapping Issue | Major | P1 | QA | Closed |  | 10 minutes | [6 empty] | Discussed with halancia
13 | 25-10-2017 | 02-08-2017 | World Avenues | Client | Calls/Meeting | WA-10 | Booking | I1008208 ( Modify of curremcy of bopoking) | Critical | P1 | Dev | ReOpned |  | 45 minutes
14 | 25-10-2017 | 08-09-2017 | Asian Overland | Client | Task | AOS-237 | Registration | QTECH - agent username characters | Major | P2 | QA | Closed |  | 30 minutes
1 | 26-10-2017 | 11-09-2017 | Asian Overland | QA | Bug | AOS-253 | Search | Date display Issue | Critical | P1 | Dev | Open |  | 30 minutes |  | 25-10-2017 |  | 26-10-2017 | 26-10-2017 | 26-10-2017
2 | 26-10-2017 | 07-10-2017 | World Avenues | QA | Bug | OTR-310 | Upload Document | Uploaded successfully but not displayed for Agent, Supplier and Booking | Critical | P1 | QA | Closed |  | 15 minutes |  |  |  | 26-10-2017 | 26-10-2017 | 26-10-2017
3 | 26-10-2017 | 07-10-2017 | World Avenues | QA | Bug | OTR-308 | Upload Document | Option Other : Change the text | Medium | P2 | QA | Closed |  | 15 minutes |  |  |  | 26-10-2017 | 26-10-2017 | 26-10-2017
4 | 26-10-2017 | 07-10-2017 | World Avenues | QA | Bug | OTR-307 | Upload Document | Option hide and scroll bar not required | Major | P2 | QA | Closed |  | 10 minutes |  |  |  | 26-10-2017 | 26-10-2017 | 26-10-2017
5 | 26-10-2017 | 16-10-2017 | World Avenues | Client | Client Issue | WA-174 | Supplier | W2M Performance | Major | P2 | Client | InProgress |  | 1 hour | 17-10-2017 | 17-10-2017
6 | 26-10-2017 | 26-10-2017 | Product | PM | Calls/Meeting |  |  | Team Scrum Meeting & Issue disucssion | Major |  |  | Closed |  | 30 minutes
7 | 26-10-2017 | 26-10-2017 | Pardisan | QA | Calls/Meeting |  | Packages | Pardisan Packages new implementation | Major | P2 | QA | Closed |  | 20 minutes
8 | 26-10-2017 | 29-08-2017 | World Avenues | QA | Bug | WA-82 | Supplier | Hilton New Integration | Critical | P1 | Dev | ReOpned |  | 1 hour | 30-09-2017 | 02-10-2017 | 10-10-2017
9 | 26-10-2017 | 29-08-2017 | Product | Client | Calls/Meeting |  | Search | WTM ¦ Frequent Issues facing with suppliers | Major | P2 | QA | Closed |  | 15 minutes
10 | 26-10-2017 | 02-08-2017 | World Avenues | Client | Client Issue | WA-10 | Booking | I1008208 ( Modify of curremcy of bopoking) | Critical | P1 | Dev | Closed |  | 30 minutes |  |  |  | 26-10-2017 | 26-10-2017 | 26-10-2017
11 | 26-10-2017 | 25-10-2017 | World Avenues | Client | Calls/Meeting | WA-188 | Booking | Modify button | Major | P2 | QA | Closed |  | 30 minutes |  |  |  | 26-10-2017 | 26-10-2017 | 26-10-2017
12 | 26-10-2017 | 18-10-2017 | World Avenues | Client | Client Issue | WA-176 | Booking | USD EXCHANGE RATE IN TOUR SHEET 01-10-17 TO 17-10-17 | Critical | P1 | Client | OnHold |  | 30 minutes |  | 18-10-2017 |  |  |  |  | Awaiting for client response
13